CITYHOSPITAL — HYDERABAD

AGILE / SCRUM PROJECT DOCUMENT

Appointment No-Show Reduction Initiative

| Field | Details |
| --- | --- |
| Methodology | Agile Scrum — 2-Week Sprints |
| Product Owner | Ms. Priya Sharma (Operations Head) |
| Scrum Master / BA | Senior BA — Hospital Operations |
| Development Team | 5 Developers + 2 QA Engineers |
| Sprint Duration | 2 Weeks |
| Total Sprints | 4 Sprints = 8 Weeks |
| Project Start | March 3, 2026 |
| Go-Live Target | April 24, 2026 |

# 1. Scrum Team

| Role | Person | Responsibilities |
| --- | --- | --- |
| Product Owner | Ms. Priya Sharma | Owns Product Backlog. Prioritizes user stories. Accepts completed work. Represents hospital management. |
| Scrum Master / BA | Senior BA | Facilitates all ceremonies. Removes blockers. Writes user stories and acceptance criteria. Documents requirements. |
| Backend Developer (Lead) | Arjun Reddy | Reminder engine API, patient database integration, IVR integration, reschedule portal backend. |
| Backend Developer | Kavitha Nair | High-risk patient flagging system, no-show reason capture API, slot recovery automation. |
| Backend Developer | Suresh Babu | Operations dashboard data pipeline, weekly report automation, alert rule engine. |
| Frontend Developer | Meera Iyer | Patient portal UI (reschedule/cancel), reminder preference settings, mobile app screens. |
| Frontend Developer | Ravi Patel | Hospital operations dashboard UI, KPI widgets, department filters, trend charts. |
| QA Engineer | Anita Kumar | Test planning, test case writing, regression testing, UAT coordination. |
| QA Engineer | Deepak Sharma | Performance testing, mobile app testing, API contract testing. |

# 2. Product Backlog

All 14 user stories prioritized using MoSCoW. Product Owner owns and maintains this backlog.

| ID | User Story | Acceptance Criteria (Summary) | Priority | Points | Sprint |
| --- | --- | --- | --- | --- | --- |
| US-001 | As a patient, I want to receive an SMS reminder 24 hours before my appointment so I do not forget. | SMS sent 24 hrs before. Contains doctor name, time, dept, address, reschedule link. | Must Have | 5 | 1 |
| US-002 | As a patient, I want a second SMS reminder 2 hours before my appointment as a final alert. | Second SMS sent 2 hrs before. Contains same details + directions link. | Must Have | 3 | 1 |
| US-003 | As a patient who prefers calls, I want an automated IVR call reminder 24 hours before my appointment. | IVR call triggers 24 hrs before. Message confirms appointment details. Option to press 1 to confirm or 2 to reschedule. | Must Have | 8 | 1 |
| US-004 | As a patient, I want to reschedule my appointment online up to 4 hours before the appointment without any penalty. | Online reschedule portal accessible via SMS link. Shows available slots. Confirms new slot via SMS. | Must Have | 13 | 2 |
| US-005 | As a patient, I want to cancel my appointment online and free the slot for another patient. | Cancel option in portal. Mandatory reason selection. Slot released immediately. Confirmation SMS sent. | Must Have | 8 | 2 |
| US-006 | As a patient who missed my appointment, I want to receive an automatic SMS within 2 hours offering to reschedule. | Auto-SMS sent 2 hrs after no-show detected. Contains reschedule link. Tracked if patient reschedules. | Should Have | 5 | 2 |
| US-007 | As the hospital system, patients with 2 or more no-shows in 6 months must be flagged as high-risk automatically. | Flagging job runs nightly. High-risk flag stored in patient profile. Flag triggers extra phone call outreach. | Should Have | 8 | 3 |
| US-008 | As the reception team, I want to see a list of high-risk patients for today's appointments so I can call them proactively. | High-risk patient list available in receptionist dashboard by 7 AM daily. Click-to-call functionality. | Should Have | 5 | 3 |
| US-009 | As the system, every no-show must capture a mandatory reason — either via patient SMS response or receptionist input. | No-show reason collected via SMS reply option or receptionist dropdown. 100% capture rate required. | Must Have | 5 | 2 |
| US-010 | As a hospital manager, I want a live dashboard showing today's no-show rate by department and doctor in real time. | Dashboard refreshes every 30 min. Filterable by dept, doctor, date. Exportable to Excel. | Should Have | 13 | 3 |
| US-011 | As a hospital manager, I want an automated alert when any department's no-show rate exceeds 20% on a given day. | Alert sent via email + WhatsApp to ops head. Triggered when dept rate > 20%. Includes dept name and current count. | Should Have | 8 | 3 |
| US-012 | As a patient, I want to set my reminder preference (SMS, call, or both) in the patient portal so I get reminders in my preferred way. | Preference settings page in portal. Default is SMS. Change persists for all future appointments. | Could Have | 5 | 4 |
| US-013 | As a hospital manager, I want a weekly no-show trend report emailed automatically every Monday morning. | Email sent by 7 AM Monday. PDF attachment with dept comparison, trend chart, and top no-show reasons. | Could Have | 8 | 4 |
| US-014 | As the finance team, I want to see monthly revenue impact of no-shows with trend comparison to previous month. | Finance report available in dashboard. Shows lost revenue estimate, trend, and recovery estimate. | Could Have | 5 | 4 |

# 3. Sprint Plan

## SPRINT 1 — Reminder Engine (March 3–14, 2026)

Sprint Goal: Every patient receives at least one automated reminder before their appointment. Target: reduce 'forgot' no-shows by 60%.

| Task | Story | Owner | Days | Status |
| --- | --- | --- | --- | --- |
| Build patient reminder scheduler — reads appointment DB, triggers reminders 24 hrs before | US-001 | Arjun Reddy | 3 | To Do |
| Integrate SMS gateway (Twilio or MSG91) — send appointment reminder SMS | US-001 | Arjun Reddy | 2 | To Do |
| Build 2-hour reminder job — second SMS trigger 2 hours before appointment | US-002 | Kavitha Nair | 1 | To Do |
| Build IVR call integration — automated voice call with appointment confirmation | US-003 | Arjun Reddy | 3 | To Do |
| Add reschedule link to SMS — dynamic URL with appointment ID token | US-001, US-004 | Meera Iyer | 1 | To Do |
| QA: Test all reminder types for 20 sample appointments in staging | US-001,002,003 | Anita Kumar | 3 | To Do |
| QA: Test SMS delivery failures — retry logic validation | US-001 | Deepak Sharma | 2 | To Do |
| Sprint 1 integration testing + demo preparation | All | Full Team | 1 | To Do |

Sprint 1 Points: 16  |  Expected Impact: No-show rate drops from 28.2% to ~18% (28% of no-shows caused by forgetting)

## SPRINT 2 — Reschedule Portal + No-Show Recovery (March 17–28, 2026)

Sprint Goal: Patients can self-serve reschedule or cancel. Every no-show gets a recovery SMS. Reason capture 100%.

| Task | Story | Owner | Days | Status |
| --- | --- | --- | --- | --- |
| Build patient portal — reschedule flow (slot selection, confirm, SMS) | US-004 | Meera Iyer | 4 | To Do |
| Build cancellation flow in portal — reason dropdown, slot release, confirmation SMS | US-005 | Meera Iyer | 2 | To Do |
| Build no-show detection job — runs every 30 min after appointment time | US-006, US-009 | Kavitha Nair | 2 | To Do |
| Build recovery SMS trigger — send reschedule link 2 hours after no-show detected | US-006 | Kavitha Nair | 1 | To Do |
| Build no-show reason capture — SMS reply option + receptionist dropdown | US-009 | Arjun Reddy | 2 | To Do |
| QA: Reschedule portal end-to-end testing with 50 test cases | US-004, US-005 | Anita Kumar | 3 | To Do |
| QA: No-show detection accuracy testing — verify all no-shows flagged correctly | US-006, US-009 | Deepak Sharma | 2 | To Do |
| Performance test: Portal handles 200 concurrent users | US-004 | Deepak Sharma | 2 | To Do |

Sprint 2 Points: 26  |  Expected Impact: Rate drops to ~14%. Slot recovery adds 20-30% revenue recovery.

## SPRINT 3 — High-Risk Flagging + Ops Dashboard (March 31–April 11, 2026)

Sprint Goal: Hospital management has real-time visibility. High-risk patients get proactive outreach before they no-show.

| Task | Story | Owner | Days | Status |
| --- | --- | --- | --- | --- |
| Build high-risk patient flagging algorithm — flag patients with 2+ no-shows in 6 months | US-007 | Kavitha Nair | 3 | To Do |
| Build receptionist morning list — high-risk patients for today's appointments | US-008 | Ravi Patel | 2 | To Do |
| Build operations dashboard data pipeline — real-time no-show events | US-010 | Suresh Babu | 4 | To Do |
| Build dashboard UI — dept-wise no-show tiles, trend chart, doctor comparison table | US-010 | Ravi Patel | 4 | To Do |
| Build alert rule engine — email + WhatsApp when dept > 20% no-show rate | US-011 | Suresh Babu | 2 | To Do |
| QA: High-risk flag accuracy — verify patients correctly identified | US-007, US-008 | Anita Kumar | 2 | To Do |
| QA: Dashboard refresh and alert trigger testing | US-010, US-011 | Deepak Sharma | 3 | To Do |

Sprint 3 Points: 26  |  Expected Impact: Rate drops to ~11%. Management can now act in real time.

## SPRINT 4 — Could Have Features + UAT + Go-Live (April 14–24, 2026)

Sprint Goal: Deliver remaining features, complete UAT with hospital staff, fix all bugs, go live.

| Task | Story | Owner | Days | Status |
| --- | --- | --- | --- | --- |
| Build reminder preference settings in patient portal | US-012 | Meera Iyer | 2 | To Do |
| Build weekly Monday report automation — PDF email to management | US-013 | Suresh Babu | 3 | To Do |
| Build finance revenue impact report — monthly lost revenue with trend | US-014 | Suresh Babu | 2 | To Do |
| User Acceptance Testing — Reception team, Ops head, 5 test patients | All | BA + QA | 4 | To Do |
| Fix UAT bugs — all P1 and P2 bugs resolved | All | Dev Team | 2 | To Do |
| Go-Live: Enable reminder system for all departments | All | All Teams | 1 | To Do |
| Go-Live: Enable patient portal + ops dashboard | All | All Teams | 1 | To Do |
| Post-launch monitoring — 48 hours war room | All | All Teams | 2 | To Do |

Sprint 4 Points: 18  |  Target: No-show rate < 10% within 2 weeks of go-live.

# 4. Scrum Ceremonies

| Ceremony | When | Duration | Who | Output |
| --- | --- | --- | --- | --- |
| Sprint Planning | Every 2nd Monday — 10 AM | 3 hours | Full Team | Sprint backlog + sprint goal committed |
| Daily Standup | Every day — 9:30 AM | 15 minutes | Full Team | Blockers identified; progress shared |
| Backlog Refinement | Every Wednesday — 3 PM | 1 hour | PO + SM + Leads | Stories estimated and refined for next sprint |
| Sprint Review | Every 2nd Friday — 2 PM | 1 hour | Team + Stakeholders | Working features demoed; PO accepts or rejects |
| Sprint Retrospective | Every 2nd Friday — 3:30 PM | 45 minutes | Scrum Team | What went well, what to improve, action items |

# 5. Definition of Done

| # | Criterion | Checked By |
| --- | --- | --- |
| 1 | Code written, peer-reviewed, and merged to main branch | Developer + Lead |
| 2 | Unit tests written and all passing (min 80% coverage) | Developer |
| 3 | Integration tests passed in staging environment | QA Engineer |
| 4 | All acceptance criteria from user story validated | QA + BA |
| 5 | Zero P1/P2 bugs open for this story | QA Engineer |
| 6 | Product Owner has reviewed demo and formally accepted | Product Owner |
| 7 | Documentation updated if applicable | BA / Developer |
| 8 | SMS/IVR delivery success rate > 95% in staging test | QA Engineer |

# 6. Velocity & Burn-Down Plan

| Sprint | Stories | Points | Target Date | No-Show Rate Target After Sprint |
| --- | --- | --- | --- | --- |
| Sprint 1 | US-001, 002, 003 | 16 pts | Mar 14, 2026 | ~18% (from 28.2%) |
| Sprint 2 | US-004, 005, 006, 009 | 26 pts | Mar 28, 2026 | ~14% |
| Sprint 3 | US-007, 008, 010, 011 | 26 pts | Apr 11, 2026 | ~11% |
| Sprint 4 | US-012, 013, 014 + UAT | 18 pts | Apr 24, 2026 | < 10% (TARGET MET) |
| TOTAL | 14 Stories | 86 Points | 8 Weeks | From 28.2% to < 10% |

# 7. Sign-Off

| Role | Name | Approved | Date |
| --- | --- | --- | --- |
| Product Owner | Ms. Priya Sharma | ___________ | ___________ |
| Scrum Master / BA | Senior BA | ___________ | ___________ |
| Hospital Director | Dr. Mehta | ___________ | ___________ |
| IT Lead | Arjun Reddy | ___________ | ___________ |

CityHospital Pvt. Ltd.  |  Agile Scrum Document  |  v1.0  |  Confidential  |  February 2026